## Sheet1
Probability | Harm severity
| Negligible | Marginal | Critical | Catastrophic
Certain | Syntax errors prevent me from compiling my program | Either a bug caused by program logic, improper syntax or by the underlying API platform / IDE / OS that prevents the Application & development process from functioning as it should | Very high | Very high
Likely | Accidentally deploying the Application to the main branch with dev spring boot profile | High | Contract a bad case of COVID, or some other illness that prevents me from being able to code | Very high
Possible | Low | Underestimating how much time it takes to implement the features chosen and not managing my time appropriately | My computer breaks down and becomes out of commission | My accounts are hacked and compromised such that I am unable to continue working, or my data is intentionally deleted locally and remotely
Unlikely | Low | Losing my internet access from home, which is my primary location for work, and being unable to work | Mentors assigned to support me become unavailable due to sickness or other reason | My project data is all lost due to a SCM error or bad back up strategy
Rare | Low | GitHub's servers go down for some reason and I am unable to push my work to their remote repository | QA's servers go down for some reason and I am unable to communicate with mentors | Pandemic, Flooding or other disasters prevent me from working on my project
Eliminated | Eliminated

## Sheet2
Low
Assessor Name: |  | Don K. Isiko |  |  |  |  | Medium
Date of Review: |  | 2022-01-30 |  |  |  |  | High
Date created | no. | Description | Evaluation | Likelihood | Impact Level | Responsibility | Response | Control Measures (predicted) | Date of Impact | Actual Measures
2021-01-30 | 1 | Software Bug | Either a bug caused by program logic, improper syntax or by the underlying API platform / IDE / OS that prevents the Application & development process from functioning as it should | High | Low | Don Isiko | Debug, the API platform being used and IDE have thouroughly stood the test of time through countless developers, there is a plethora of information available online | Employ good practice programming principles, like SOLID, KISS, DRY and by extension design patterns to minimise the chance that something goes wrong, and maximise the ability of other programmers to follow your code intent
2021-01-30 | 2 | Configuration conflicts | Accidentally deploying the Application to the main branch with dev spring boot profile instead of the production profile | High | Low | Don Isiko | Redeploy application with correct profile | Automated testing on GitHub, all pull requests to the main branch are to be run through a GitHub action that will run the appropriate tests to ensure that the profile is correct
2021-01-30 | 3 | GitHub server out of service | GitHub's servers go down for some reason and I am unable to push my work to their remote repository | Low | Low | GitHub | Use locally stored Git repository and push it to another SCM | GitHub employ various redundancy and security protocols to ensure high availability
2021-01-30 | 4 | Not finishing on time | Underestimating how much time it takes to implement the features chosen and not managing my time appropriately | Low | Medium | Don Isiko | Submit work done to date on deadline, highlighting as much of MVP deliverables as possible | Prioritise MVP above all other features, as well as documentation and planning, once all this has been complete to a satisfactory level, only then can additional functionality/goals be prioritised
2021-01-30 | 5 | Loss of Internet connection | Losing my internet access from home, which is my primary location for work, and being unable to work | Low | Medium | Don Isiko | Work from internet café or public library | Ensure internet fees are paid
2021-01-30 | 6 | Teacher/Mentor Unavailable | Mentors assigned to support me become unavailable due to sickness or other reason | Medium | Medium | QA | Rely on Project specification to guide me on meeting deliverables, consult QA for alternative mentors | QA have reserve mentoring resources should an employee become unwell
2021-01-30 | 7 | Hardware Failure | My computer breaks down and becomes out of commission | Low | High | Don Isiko | Obtain access to another computer | Regular back up strategy, Install Antiviral software and store computer away safely after use. Keep away from liquids!
2021-01-30 | 8 | Loss of work | My project data is all lost due to a SCM error or bad back up strategy | Medium | High | Don Isiko | Restore to most recently available backup | Regular back up strategy: save at least every 5 minutes, commit at the end of every sub-task, task, or story/feature
2021-01-30 | 9 | Sickness | Contract a bad case of COVID, or some other illness that prevents me from being able to code | Medium | High | Don Isiko | Rest and take medication to maximise rate of recovery | Minimise unnecessary contact outside immediate contacts, practice good sanitation, eat balanced diet, exercise, sleep sufficiently
2021-01-30 | 10 | QA server out of service | QA's servers go down for some reason and I am unable to communicate with mentors | Low | High | QA | Rely on Project specification to guide me on meeting deliverables, consult QA for alternative mentors | QA employ various redundancy and security protocols to ensure high availability
2021-01-30 | 11 | Natural Disaster | Pandemic, Flooding or other disasters prevent me from working on my project | Low | High | N/A | Restore to most recently available backup when normal working conditions are re established | Live in a location that is not prone to natural disasters (London)
2021-01-30 | 12 | Malicious interference | My accounts are hacked and compromised such that I am unable to continue working, or my data is intentionally deleted locally and remotely | Low | High | Don Isiko | Restore to most recently available backup when normal working conditions are re established | Employ good security practices, password protection, antiviral software, regular changing of passwords, do not leave physical hardware in unsecure locations